## Launch Tracker
Verseluft Website Launch Checklist
MUST HAVE
Done | ID | Task | Estimate | Notes
FALSE | M01 | Make the site responsive on mobile, tablet, and desktop. | 4–8 hours | Check the main pages and common screen sizes.
FALSE | M02 | Temporarily hide sections that do not have content yet. | 30–90 min | Keep empty or placeholder content out of the launch experience.
FALSE | M03 | Make text at the bottom of the page readable, including its hover state. | 30–90 min | Check text/background contrast and hover styling.
FALSE | M04 | Fix broken buttons so they work or lead somewhere useful. | 1–2 hours | This refers to broken buttons generally; Contact CTAs and the Contact page button have separate items below.
FALSE | M05 | Make the intended content cards clickable. | 1–2 hours | Apply only to cards that are meant to open a page or item.
FALSE | M06 | Fix broken call-to-action buttons, including Contact CTAs. | 30–90 min | Check CTA destinations and click behavior throughout the site.
FALSE | M07 | Let visitors minimize or close the full-screen Library PDF viewer. | 2–4 hours | Preserve a clear way to return to the Library page.
FALSE | M08 | Fix the vertical text on the About Us page. | 30–60 min
FALSE | M09 | Fix the About Us layout and move the top border to its intended position. | 1–2 hours
FALSE | M10 | Fix the non-working button on the Contact page. | 30–90 min | This may overlap with M04 or M06; inspect the actual button before changing code.
FALSE | M11 | Make current projects clickable. | 1–2 hours | Link each project to its intended destination.
FALSE | M12 | Make each “View Book” button open the correct page for that book. | 1–3 hours | If a real book page does not exist, report that dependency and propose a useful destination.
FALSE | M13 | Improve the position and readability of descriptions beside titles on the home page. | 1–2 hours
FALSE | M14 | Make search behave as expected, or hide it until it is ready. | 2–4 hours | Do not leave a visible search control that does not work.
GOOD TO HAVE
Done | ID | Task | Estimate | Notes
FALSE | G01 | Adjust font sizes across the site. | 1–3 hours | Agree on a consistent type scale while preserving readability.
FALSE | G02 | Make full-page background sections consistent in size and coverage. | 1–3 hours
FALSE | G03 | Add hover animations to buttons. | 30–90 min | Keep the effect subtle and preserve keyboard focus feedback.
FALSE | G04 | Make font sizes and spacing consistent inside buttons. | 30–90 min
FALSE | G05 | Restyle About Us panels so they do not look like buttons. | 30–60 min | Keep button styling for genuinely interactive elements.
FALSE | G06 | Keep Upcoming Books in a consistent order while browsing. | 30–90 min | Preserve the intended order when the carousel advances.
FALSE | G07 | Improve the size and placement of arrows beside call-to-action buttons. | 30–90 min
FALSE | G08 | Refresh the visual design of the Projects page. | 2–5 hours | Keep project information and links easy to scan.
FALSE | G09 | Adjust the size of the numbers at the top of the Blog page. | 30–60 min
FALSE | G10 | Correct the position of the “View Book” button in the Library. | 30–60 min | Separate from M12, which fixes where the button leads.
FALSE | G11 | Put a plus sign before the statistics on the home page. | 15–30 min | Example: “90+” rather than “+90,” if that matches the intended design.